## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP).
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14
1.1 | Arm prototyping & printing | 10 |  | 15% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.2 | Assembling model | 4 |  |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2.1 | Sorter prototyping & wood cutting | 30 | [9 empty] | 100% | 100% | 100% | 100% | 100%
2.2 | Change motor (hard+soft) | 10 | [10 empty] | 100% | 100% | 100% | 100%
2.3 | Assembling model | 4 | [11 empty] | 100% | 100% | 100%
2.4 | Update code | 8 | [11 empty] | 100% | 100% | 100%
3.1 | Code the Thrower | 20 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3.2 | Electrical mounting | 20 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3.3 | Datasheet on PWM | 8 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4.1 | Executable & Initialisation fn | 20 |  |  |  | 40% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4.2 | Cleaning code, error cabling ... | 32 |  |  |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4.3 | Update all RIO cards | 4 | [5 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4.4 | Real Time | 56
5.1 | Supply PCB prototyping | 28 |  | 15% | 30% | 45% | 60% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 100% | 100%
5.2 | Data PCB Prototyping | 80 | [6 empty] | 30% | 50% | 80% | 100% | 100% | 100% | 100% | 100%
5.3 | PCB Deployment & integration | 32 | [9 empty] | 15% | 50% | 60% | 80% | 100%
6.1 | Lidar - Research & command | 8 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6.2 | Lidar - Cabling & Data sending | 80 | [9 empty] | 50% | 100% | 100% | 100% | 100%
6.3 | Lidar - Data treatment | 120 | [10 empty] | 33% | 66% | 80% | 100%
6.4 | Lidar - Integration on robot | 4 | [12 empty] | 100% | 100%
7.1 | Brainstorming Scenarii & details | 8 |  | 20% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7.2 | Scenario 1 | 16 |  |  | 40% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7.3 | Scenario 2 | 100 |  |  |  | 33% | 33% | 66% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7.4 | Scenario 3 | 18 | [12 empty] | 80% | 90%
7.5 | Scenario 4 | 58
8.1 | Preparation & Participation NI | 40 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9.1 | Weekly & project management | 212 | 6% | 12% | 18% | 24% | 30% | 36% | 42% | 48% | 54% | 60% | 66% | 72% | 75% | 100%
10.1 | Handover | 212: 8; 100%: 100%
11.1 | JPO presentation | 32 | [6 empty] | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100%
Insert new rows above this one
|  | Cumulative EV | 52.72 | 112.74 | 153.96 | 226.48 | 267.4 | 346.72 | 433.44 | 470.16 | 506.88 | 610.4 | 723.92 | 791.44 | 861 | 954.2

## Report
Robot NI
Earned Value Analysis Report
| Prepared By: | COURT Nicolas
| Date: | 2019-03-08
[42]
| For Period: | 2018-2019
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | BAC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | ← You can change the labels for the periods (e.g. Week 1/2/3, Jan/Feb/Mar, etc.)
1.1 | Arm prototyping & printing | 10 |  | 2 | 4 | 4 | [10 empty] | ← Enter or edit values in the light-blue cells.
1.2 | Assembling model | 4 |  |  |  |  | 4
2.1 | Sorter prototyping & wood cutting | 30 | [9 empty] | 30
2.2 | Change motor (hard+soft) | 10 | [10 empty] | 10
2.3 | Assembling model | 4 | [11 empty] | 4
2.4 | Update code | 8 | [11 empty] | 8
3.1 | Code the Thrower | 20 |  | 20
3.2 | Electrical mounting | 20 |  | 20
3.3 | Datasheet on PWM | 8 |  |  | 8
4.1 | Executable & Initialisation fn | 20 |  |  |  | 8 | 4 | 8
4.2 | Cleaning code, error cabling ... | 32 |  |  |  |  | 16 | 16
4.3 | Update all RIO cards | 4 | [5 empty] | 4
4.4 | Real Time | 56 | [5 empty] | 56
5.1 | Supply PCB prototyping | 28 |  | 4 | 4 | 8 | 4 | [8 empty] | 8
5.2 | Data PCB Prototyping | 80 | [5 empty] | 8 | 8 | 32 | 32
5.3 | PCB Deployment & integration | 32 | [9 empty] | 4 | 4 | 4 | 4 | 16
6.1 | Lidar - Research & command | 8 | [7 empty] | 8
6.2 | Lidar - Cabling & Data sending | 80 | [9 empty] | 40 | 40
6.3 | Lidar - Data treatment | 120 | [9 empty] | 40 | 40 | 16 | 16 | 8
6.4 | Lidar - Integration on robot | 4 | [12 empty] | 4
7.1 | Brainstorming Scenarii & details | 8 |  | 8
7.2 | Scenario 1 | 16 |  | 8 | 8
7.3 | Scenario 2 | 100 |  |  | 16 |  | 4 | 32 | [6 empty] | 32 | 16
7.4 | Scenario 3 | 18 |  |  | 8 | [9 empty] | 10
7.5 | Scenario 4 | 58 | [9 empty] | 2 | 40 |  | 16
8.1 | Preparation & Participation NI | 40 | 40
9.1 | Weekly & project management | 212 |  | 16 | 32 | 16 | 8 | 12 | 8 | 32 | 8 | 8 | 8 | 8 | 8 | 48
10.1 | Handover | 8 | [13 empty] | 8
11.1 | JPO presentation | 32 | [5 empty] | 12 | 10 | [5 empty] | 10
Insert new rows above this one | [16 empty] | ← To add more tasks, insert rows above this one. You can or delete this row after you are done adding tasks.
| Total Budgeted Cost at Completion | 1070 | 40 | 78 | 80 | 36 | 40 | 148 | 26 | 72 | 40 | 124 | 142 | 40 | 100 | 104
|  | Cumulative Planned Value (PV) | 40 | 118 | 198 | 234 | 274 | 422 | 448 | 520 | 560 | 684 | 826 | 866 | 966 | 1070
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 45 | 125 | 205 | 245 | 293 | 425 | 467 | 535 | 577 | 695 | 837 | 869 | 951 | 1055 | ← Enter the Actual Costs as calculated from the AC worksheet.
|  | Cumulative Earned Value (EV) | 52.72 | 112.74 | 153.96 | 226.48 | 267.4 | 346.72 | 433.44 | 470.16 | 506.88 | 610.4 | 723.92 | 791.44 | 861 | 954.2 | ← Enter the Earned Value as calculated from the EV worksheet.
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | 7.72 | -12.26 | -51.04 | -18.52 | -25.6 | -78.28 | -33.56 | -64.84 | -70.12 | -84.6 | -113.08 | -77.56 | -90 | -100.8
|  | Schedule Variance (SV = EV - PV) | 12.72 | -5.26 | -44.04 | -7.52 | -6.6 | -75.28 | -14.56 | -49.84 | -53.12 | -73.6 | -102.08 | -74.56 | -105 | -115.8
|  | Cost Performance Index (CPI = EV/AC) | 1.1716 | 0.90192 | 0.75102 | 0.92441 | 0.91263 | 0.81581 | 0.92814 | 0.8788 | 0.87847 | 0.87827 | 0.8649 | 0.91075 | 0.90536 | 0.90445
|  | Schedule Performance Index (SPI = EV/PV) | 1.318 | 0.95542 | 0.77758 | 0.96786 | 0.97591 | 0.82161 | 0.9675 | 0.90415 | 0.90514 | 0.8924 | 0.87642 | 0.9139 | 0.8913 | 0.89178
|  | Estimated Cost at Completion (EAC) | 913.3156 | 1186.358 | 1424.7207 | 1157.4974 | 1172.4383 | 1311.5771 | 1152.847 | 1217.5642 | 1218.02 | 1218.2995 | 1237.1395 | 1174.8585 | 1181.8467 | 1183.0329
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost at Completion

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and BAC (Budget at Completion) are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14
1.1 | Arm prototyping & printing |  | Wk 2: 2; Wk 3: 4; Wk 4: 4
1.2 | Assembling model |  | Wk 5: 4
2.1 | Sorter prototyping & wood cutting |  | Wk 10: 30
2.2 | Change motor (hard+soft) |  | Wk 11: 20
2.3 | Assembling model |  | Wk 12: 4
2.4 | Update code |  | Wk 12: 8
3.1 | Code the Thrower |  | Wk 2: 20
3.2 | Electrical mounting |  | Wk 2: 20
3.3 | Datasheet on PWM |  | Wk 3: 8
4.1 | Executable & Initialisation fn |  | Wk 4: 8; Wk 5: 4; Wk 6: 8
4.2 | Cleaning code, error cabling ... |  | Wk 5: 16; Wk 6: 16
4.3 | Update all RIO cards |  | Wk 6: 8
4.4 | Real Time
5.1 | Supply PCB prototyping |  | Wk 2: 10; Wk 3: 12; Wk 4: 12; Wk 5: 12; Wk 6: 16; Wk 11: 16; Wk 14: 8
5.2 | Data PCB Prototyping |  | Wk 7: 8; Wk 8: 32; Wk 9: 32
5.3 | PCB Deployment & integration |  | Wk 10: 8; Wk 11: 16; Wk 12: 8; Wk 13: 12; Wk 14: 16
6.1 | Lidar - Research & command |  | Wk 8: 4; Wk 9: 2
6.2 | Lidar - Cabling & Data sending |  | Wk 10: 40; Wk 11: 42
6.3 | Lidar - Data treatment |  | Wk 10: 32; Wk 11: 40; Wk 12: 8; Wk 13: 8; Wk 14: 8
6.4 | Lidar - Integration on robot |  | Wk 13: 2
7.1 | Brainstorming Scenarii & details |  | Wk 2: 4
7.2 | Scenario 1 |  | Wk 3: 8; Wk 6: 8
7.3 | Scenario 2 |  | Wk 3: 16; Wk 4: 8; Wk 5: 4; Wk 6: 60; Wk 13: 32; Wk 14: 16
7.4 | Scenario 3 |  | Wk 13: 10
7.5 | Scenario 4
8.1 | Preparation & Participation NI |  | Wk 1: 45
9.1 | Weekly & project management |  |  | 24 | 32 | 8 | 8 | 12 | 4 | 32 | 8 | 8 | 8 | 4 | 8 | 48
10.1 | Handover |  | Wk 14: 8
11.1 | JPO presentation |  | Wk 6: 4; Wk 7: 30; Wk 13: 10
Insert new rows above this one
|  | Total Actual Cost | 45 | 80 | 80 | 40 | 48 | 132 | 42 | 68 | 42 | 118 | 142 | 32 | 82 | 104
|  | Cumulative Actual Cost (AC) | 45 | 125 | 205 | 245 | 293 | 425 | 467 | 535 | 577 | 695 | 837 | 869 | 951 | 1055